## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Green
Kelham island VR project
Project start date: | 2022-06-06 | [10 empty] | Scrolling increment: | [5 empty] | 0
Milestone marker: | 1 | 1 |  |  | June | [27 empty] | July
 | time axis 2022-06-06 to 2022-07-31
Milestone description | Assigned to | Progress | Start | Days | time axis 2022-06-06 to 2022-07-31
Project set up
Time plan |  |  | 2022-06-06 | 3
Folder structure |  |  | 2022-06-06 | 3
VR project setup and documentation |  |  | 2022-06-06 | 5
Documentation set up |  |  | 2022-06-06 | 4
File saving a backup system setup |  |  | 2022-06-06 | 3
Assets
Obtain audio assets |  |  | 2022-06-06 | 7
Create 3d models for the exhibits |  |  | 2022-06-06 | 21
Create 3d models for the enviroment |  |  | 2022-06-08 | 10
Create 3d models for the users arms and hands |  |  | 2022-06-13 | 5
Obtain image texture assets |  |  | 2022-06-15 | 14
Project creation
Create a start menu and a way to transition into the experience |  |  | 2022-06-20 | 5
Create a 3d enviroment for the user to move around in |  |  | 2022-06-22 | 14
Create a building using the 3d models which were created for the enviroment, and set up collisions to keep the user inside |  |  | 2022-07-11 | 7
Arrange the 3d models for the exhibits in the building |  |  | 2022-06-22 | 3
Create a script to allow the user to interact with the exhibits |  |  | 2022-06-22 | 3
Title 4
Task 1 |  |  | 2022-07-13 | 15
Task 2 |  |  | 2022-07-05 | 5
Task 3 |  |  | 2022-08-25 | 5
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Blue
Project title
Company name
Project lead
Project start date: | 2022-06-03 | [10 empty] | Scrolling increment: | [5 empty] | 13
Milestone marker: | 1 | 1 |  |  | June | [20 empty] | July | [27 empty] | August
 | time axis 2022-06-16 to 2022-08-10
Milestone description | Assigned to | Progress | Start | Days | time axis 2022-06-16 to 2022-08-10
Title 1
Task 1 |  | 25% | 2022-06-06 | 3
Task 2 |  |  | 2022-06-11 | 1
Task 3 |  | 50% | 2022-06-03 | 10
Task 4 |  |  | 2022-06-26 | 1 | bar: 2022-06-26
Task 5 |  | 10% | 2022-06-12 | 6
Title 2
Task 1 |  | 60% | 2022-06-12 | 13
Task 2 |  | 50% | 2022-06-13 | 9
Task 3 |  | 33% | 2022-06-21 | 11
Task 4 |  |  | 2022-06-30 | 1 | bar: 2022-06-30
Task 5 |  |  | 2022-07-01 | 24
Title 3
Task 1 |  |  | 2022-06-21 | 4
Task 2 |  |  | 2022-06-25 | 14
Task 3 |  |  | 2022-07-11 | 6
Task 4 |  |  | 2022-07-24 | 3
Task 5 |  |  | 2022-07-16 | 19
Title 4
Task 1 |  |  | 2022-07-13 | 15
Task 2 |  |  | 2022-07-05 | 5
Task 3 |  |  | 2022-08-25 | 5
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Purple
Project title
Company name
Project lead
Project start date: | 2022-06-06 | [10 empty] | Scrolling increment: | [5 empty] | 0
Milestone marker: | 1 | 1 |  |  | June | [27 empty] | July
 | time axis 2022-06-06 to 2022-07-31
Milestone description | Assigned to | Progress | Start | Days | time axis 2022-06-06 to 2022-07-31
Project set up
Time plan |  |  | 2022-06-06 | 3
Folder structure |  |  | 2022-06-06 | 3
VR project setup and documentation |  |  | 2022-06-06 | 5
Documentation set up |  |  | 2022-06-06 | 4
File saving a backup system setup |  |  | 2022-06-06 | 3
Assets
Obtain audio assets |  |  | 2022-06-06 | 7
Create 3d models for the exhibits |  |  | 2022-06-06 | 21
Create 3d models for the enviroment |  |  | 2022-06-08 | 10
Create 3d models for the users arms and hands |  |  | 2022-06-13 | 5
Obtain image texture assets |  |  | 2022-06-15 | 14
Project creation
Create a start menu and a way to transition into the experience |  |  | 2022-06-20 | 5
Create a 3d enviroment for the user to move around in |  |  | 2022-06-22 | 14
Create a building using the 3d models which were created for the enviroment, and set up collisions to keep the user inside |  |  | 2022-07-11 | 7
Arrange the 3d models for the exhibits in the building |  |  | 2022-06-22 | 3
Create a script to allow the user to interact with the exhibits |  |  | 2022-06-22 | 3
Title 4
Task 1 |  |  | 2022-07-13 | 15
Task 2 |  |  | 2022-07-05 | 5
Task 3 |  |  | 2022-08-25 | 5
Task 4
Task 5
To add more data, Insert new rows ABOVE this one